## Summary
TT Izmir5G PLAN TOTAL
| Target | Actual | % | Week08 | Week09 | ∆
5G | 14
RF STATUS
RF Equipment (BTS@DBS) Received | 14 | 12 | 85.71% | 12 | 12 | 0
RF Installation Started | 14 | 11 | 78.57% | 11 | 11 | 0
RF Installation Finished | 14 | 11 | 78.57% | 11 | 11 | 0
QC(Closed) | 14 | 0 | 0% | 0 | 0 | 0
Acceptance | 14 | 0 | 0% | 0 | 0 | 0
TT İzmir STANDALONE PLAN TOTAL
| Target | Actual | % | Week08 | Week09 | ∆
STANDALONE | 22
RF STATUS
RF Equipment (BTS@DBS) Received | 22 | 22 | 0% | 22 | 22 | 0
RF Installation Started | 22 | 22 | 0% | 22 | 22 | 0
RF Installation Finished | 22 | 22 | 0% | 22 | 22 | 0
Acceptance | 22 | 0 | 0% | 0 | 0 | 0
PO Status(Closed) | 22 | 0 | 0% | 0 | 0 | 0
TT İzmir LTE PLAN TOTAL
| Target | Actual | % | Week08 | Week09 | ∆
LTE | 73
RF STATUS
RF Equipment (BTS@DBS) Received | 73 | 73 | 0% | 73 | 73 | 0
RF Installation Started | 73 | 73 | 0% | 73 | 73 | 0
RF Installation Finished | 73 | 71 | 0% | 71 | 71 | 0
Acceptance | 73 | 0 | 0% | 0 | 0 | 0
PO Status(Closed) | 73 | 0 | 0% | 0 | 0 | 0

## Standalone
Site Type | Project Code | Project Name | Site Code | Malzeme Status | İL | RF Subcon | RF Started Date | RF Finished Date | RF Note | TSS Subcon | TSS Prepared | TSSR Subcon | TSSR Prepared(Sent to HW) | TSSR Approved | LOS Subcon | LOS Approved | BTK Subcon | BTK Applied | BTK Approved | GS Status | Atlas Status | AsBuilt | Acceptance Docs | PAC | Survey Note | HAKKEDİŞ | BTK ANTEN | MONTAJ ANTEN
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | AI1117_NS_AE | 2025-12-22 | AYDIN | Hasan | OK | OK |  | ŞİMŞEK HABERLEŞME | 2025-11-12 | SURVEYTEAM | 2025-12-18 |  | SURVEYTEAM | 2026-01-12 | SURVEYTEAM | 2025-12-29 | 2025-01-03 | [5 empty] | 7.01.2026 tarihinde cevher girişi yapılmıştır. | 2025-12-30
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ3552_NS_AE | 5.02.2026 | İzmir | UBS | OK | OK |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | AI0157_NS_AE | 2025-08-28 | AYDIN | HASAN TÜRÜDÜ | 2025-09-01 | 2025-09-01 | SNTOOL VE HORİZON YAPILACAK.TRS ve enerji taskları kapatılmalı | ŞİMŞEK HABERLEŞME | 2025-08-14 | ALKOM | 2025-08-14 | 2025-09-15 | ŞİMŞEK HABERLEŞME | 2025-09-04 | ALKOM | 2025-08-18 | 2025-09-01 | OK | WASBUILT | OK |  |  | Cevher girişi 2.09.2025de yapıldı | 2025-09-30 | ASI4518R37v07 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | DE0366_NS_AE | 1.09.2025/22.01.2026 | DENİZLİ | SONER TURAN | 2025-09-24 | 2025-09-28 | TRS ve enerji taskları kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  | 29.09.20225 te cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ1630_NS_AE | 2025-08-28 | İZMİR | MURAT YAZICI | 2025-09-01 | 2025-09-01 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  | 07.11.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ2108_NS_AE | Malzeme Bekler | İZMİR | GETES Yaptı | GETES Yaptı | GETES Yaptı | GETES Yaptı | ŞİMŞEK HABERLEŞME | 2025-08-14 | ALKOM | 2025-12-17 |  | ŞİMŞEK HABERLEŞME | 2025-09-10 | ALKOM | 2025-12-18 | 2025-12-24 | OK | SVTAPP |  |  |  | TEKRAR (REVİZE EDİLDİ KOORDİNAT ).25.12.2025 tarihinde cevher girişi yapılmıştır. | 30.09.2025/30.12.2025 tarihinde 2 kez dosya hazırlandı ödeme yapıldı | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ2878_NS_AE | Malzeme Bekler | İZMİR | GETES Yaptı | GETES Yaptı | GETES Yaptı | GETES Yaptı | ŞİMŞEK HABERLEŞME | 2025-07-31 | ALKOM | 2025-09-05 | 2025-09-05 | ŞİMŞEK HABERLEŞME | 2025-09-08 | ALKOM | 2025-09-22 | 2025-10-13 | OK | SVTAPP |  |  |  | 14.10.2025 tarihinde cevher girişi yapıldı. | 2025-09-30 | AQU4518R23v06
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ4792_NS_AE | 2025-08-29 | İZMİR | SONER TURAN | 2025-09-03 | 2025-11-07 | TRS taskı kapatılmalı.REJECT edilmiş kontrol edilecek | ŞİMŞEK HABERLEŞME | 2025-08-01 | ALKOM | 2025-08-14 | 2025-08-29 | ŞİMŞEK HABERLEŞME | 2025-09-04 | ALKOM | 2025-12-02 | 2025-12-03 |  | ACCAPP |  |  |  | Cevher girişi 3.12.2025 te yapıldı. | 2025-09-30 | ASI4518R37v07 | AQU4518R23v06
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MN0426_NS_AE | 2025-10-21 | MANİSA | MURAT YAZICI | 2025-11-12 | 2025-11-18 | TRS ve enerji taskları kapatılmalı | ŞİMŞEK HABERLEŞME | 2025-08-19 | ALKOM | 2025-11-07 |  | ŞİMŞEK HABERLEŞME | 2025-09-12 | ALKOM | 2025-12-02 | 2025-12-03 |  | WTSS |  |  |  | Cevher girişi 3.12.2025 te yapıldı. | 2025-10-30 | ASI4518R37v07 | AQU4518R23v06
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU0709_NS_AE | 2025-09-23 | MUĞLA | HASAN TÜRÜDÜ | 2025-10-15 | 2025-10-16 | TRS ve enerji taskları kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 20.10.2025 tarihinde cevher girişi yapılmıştır. |  | AQU4518R23v06 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU0734_NS_AE | Malzeme Bekler | MUĞLA | ŞİMŞEK HABERLEŞME | 2025-10-04 | 2026-01-08 | 8.09.2025 tarihinde gelen malzemeler MU0706 sahasına str yapıldı .GİZLEME/Halk tepkisinden dolayı RF montajı yapılamadı .REJECT edilmiş kontrol edilecek | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | ASI4518R37v07 | COMBA
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU2494_NS_AE | 2025-08-22 | MUĞLA | HASAN TÜRÜDÜ | 2025-10-06 | 2025-12-05 | 28.08.205 tarihinde gelen malzemeler MU1069 sahasına str yapıldı .TRS ve enerji taskları kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 14.09.2025 tarihinde cevher girişi yapılmıştır. |  | ASI4518R37v07 | AOC4518R23v06
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU2531_NS_AE | 2025-09-23 | MUĞLA | HASAN TÜRÜDÜ | 2025-10-27 | 2025-11-16 | TRS ve enerji taskları kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 20.10.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU2645_NS_AE | MU0733 sahasından str yapıldı /22.01.2026 | MUĞLA | SONER TURAN | 2025-09-08 | 2025-09-11 | TRS taskı kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  | 13.10.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU3635_NS_AE | 28.08.2025/22.01.2026 | MUĞLA | ŞİMŞEK HABERLEŞME | 2025-09-30 | 2026-01-08 | Lampost. 12mt/Kazı yapıldı.REJECT edilmiş kontrol edilecek | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU2497_NS_AE | 2025-09-26 | MUĞLA | PAŞA TEKNOLOJİ | 2025-09-30 | 2026-01-30 | GİZLEMEbitti fakat belediye sahayı mühürlemiş. | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 22.09.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | COMBA
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU0706_NS_AE | MU0734 sahasından str yapıldı | MUĞLA | HASAN TÜRÜDÜ | 2025-09-08 | 2025-09-20 | TRS ve enerji taskları kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  |  |  | ASI4518R37v07 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | MU1069_NS_AE | MU2494 sahasından str yapıldı/22.01.2026 | MUĞLA | HASAN TÜRÜDÜ | 2025-09-09 | 2025-09-25 | TRS ve enerji taskları kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ1548_NS_AE | Malzeme Bekler | İZMİR | SONER TURAN | 2025-12-14 | 2025-12-29 | Task ilerletme bekler | ŞİMŞEK HABERLEŞME | 2025-10-20 | ALKOM | 2025-10-21 | 2025-11-03 | ALKOM | 2025-12-23 | ALKOM | 2026-01-23 | 2026-01-27 | [5 empty] | 28.01.2026 cevher girişi yapıldı | 2025-10-30 | ASI4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ6427_NS_AE | 4.12.2025/22.01.2026 | İZMİR | SONER TURAN | 2025-12-10 | 2025-12-29 | Task ilerletme bekler | ŞİMŞEK HABERLEŞME | 2025-10-20 | ALKOM | 2025-10-21 | 2025-11-04 | ALKOM | 2025-12-03 | ALKOM | 2026-01-16 | 2026-01-20 |  | WTSS |  |  |  | 21.01.2026 tarihinde cevher girişi yapılmıştır. | 30.10.2025/30.12.2025 tarihinde 2 kez dosya hazırlandı ödeme yapıldı | AOC4518R37v06 | AOC4518R37v06
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | IZ1451_NS_AE | 21.10.2025/22.01.2026 | İZMİR | MURAT YAZICI | 2025-11-08 | 2025-11-29 | TRS ve enerji taskları kapatılmalı | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | OK | 00.00.00 |  |  |  | 26.10.2025 te cevher girişi yapılmış. |  | ASI4518R37v07 | AOC4518R37v07
STANDALONE | 56A0QEF | Turk Telekom Wireless Project | AI1102_NS_AE | 2026-01-22 | UŞAK | SONER TURAN | 2025-11-30 | 2025-11-29 | Task ilerletme bekler | ŞİMŞEK HABERLEŞME | 2025-11-04 | ALKOM | 2026-01-08 | 2025-12-24 | ALKOM | 2025-12-02 | ALKOM | 2026-01-16 | 2026-01-20 | [5 empty] | 21.01.2026 tarihinde cevher girişi yapılmıştır. | 2025-12-05 | AOC4518R37v06 | AOC4518R37v06

## LTE
IZ | Project Code | Site Code | İL | Malzeme Status | RF Subcon | RF Started Date | RF Finished Date | RF Note | QC Status | TSS Subcon | TSS Prepared | TSSR Subcon | TSSR Prepared(Sent to HW) | TSSR Approved | LOS Subcon | BTK Subcon | BTK Prepared | BTK Approved | GS Status | Atlas Status | AsBuilt | Acceptance Docs | PAC | Survey Note | HAKKEDİŞ | BTK ANTEN | MONTAJ ANTEN
LTE | 56A0QEF | IZ1274_L800_AE |  | OK | 2kx | OK | OK |  | Ok
LTE | 56A0QEF | IZ0337_L800_AE |  | OK | 2kx | OK |  | Montaj Tamamlanacak.
LTE | 56A0QEF | IZ0337_L260000_AE |  | OK | 2kx | OK |  | Montaj Tamamlanacak.
LTE | 56A0QEF | AI0066_L800_AE | AYDIN | 2025-08-21 | HASAN TÜRÜDÜ | 2025-08-26 | 2025-08-28 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  | AHP4518R10v06 | AHP4518R10v06
LTE_New | 56A0QEF | AI0157_L1800_AE | AYDIN | 2025-08-21 | HASAN TÜRÜDÜ | 2025-11-15 | 2025-11-19 |  | ŞİMŞEK HABERLEŞME | 2025-08-14 | ALKOM | 2025-08-14 | 2025-09-15 | Huawei | 00.00.00 | ALKOM | 2025-08-18 | 2025-09-01 | OK | INSTALL |  |  |  | Cevher girişi 2.09.2025de yapıldı | 2025-09-30 | ASI4518R37v07 | ASI4518R37v07
LTE_New | 56A0QEF | AI4872_L1800_AE | AYDIN | 2025-09-08 |  | 2025-12-15 | 2026-02-08 |  | ŞİMŞEK HABERLEŞME | 2025-08-14 | ALKOM | 2025-09-08 | 2025-09-18 | Huawei | 00.00.00 | ALKOM | 2026-01-30 | 2026-02-14 |  | INSTALL |  |  |  | 16.02.2026 tarihinde cevher girildi | 2025-09-30 | AQU4517R4
LTE | 56A0QEF | AI5095_L800_AE | AYDIN | 2025-08-21 | HASAN TÜRÜDÜ | 2025-09-02 | 2025-09-02 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  | AQU4517R4 | AQU4517R4
LTE_New | 56A0QEF | DE0366_L1800_AE | DENİZLİ | 2025-09-01 | ŞİMŞEK HABERLEŞME | 2025-09-24 | 2025-09-27 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  | 29.09.20225 te cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
LTE | 56A0QEF | IZ0082_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-08-30 | 2025-08-30 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | AQU4517R4
LTE | 56A0QEF | IZ0129_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-09 | 2025-10-11 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R11
LTE | 56A0QEF | IZ0167_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-08-25 | 2025-08-25 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | AQU4517R4
LTE | 56A0QEF | IZ0294_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-08-24 | 2025-08-24 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | AQU4517R4
LTE | 56A0QEF | IZ0626_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-08-24 | 2025-08-24 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | AQU4517R4
LTE | 56A0QEF | IZ0697_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-10-10 | 2025-10-11 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | AQU4517R4
LTE | 56A0QEF | IZ0920_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2024-08-27 | 2025-08-27 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | ASI4518R31v06
LTE | 56A0QEF | IZ0956_L2600_AE | İZMİR | 2025-09-18 |  | 2025-10-15 | 2025-10-16 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R31v06
LTE | 56A0QEF | IZ0978_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-08-25 | 2025-08-25 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | AQU4517R4
LTE | 56A0QEF | IZ1132_L800_AE | İZMİR | 2025-08-21 |  | 2025-11-04 | 2025-11-25 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R53v07
LTE | 56A0QEF | IZ1415_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-08-24 | 2025-08-24 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | ASI4518R11
LTE_New | 56A0QEF | IZ1630_L1800_AE | İZMİR | 2025-08-21 | MURAT YAZICI | 2025-08-30 | 2025-08-31 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  | 07.11.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
LTE | 56A0QEF | IZ3051_L2600_AE | İZMİR | 2025-09-18 |  | 18.11.205 | 2025-11-19 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R53v07
LTE | 56A0QEF | IZ3185_L800_AE | İZMİR | 2025-08-21 | PAŞA TEKNOLOJİ | 2025-08-29 | 2025-08-29 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  |  |  |  | AQU4518R23v06
LTE_New | 56A0QEF | IZ4792_L1800_AE | İZMİR | 2025-08-29 |  | 2025-10-19 | 2025-10-19 | Beton atıldı. | ŞİMŞEK HABERLEŞME | 2025-08-01 | ALKOM | 2025-08-14 | 2025-08-29 | Huawei | 00.00.00 | ALKOM | 2025-12-02 | 2025-12-03 |  | SVTAPP |  |  |  | Cevher girişi 3.12.2025 te yapıldı. | 2025-09-30 | ASI4518R37v07 | AQU4518R23v06
LTE_New | 56A0QEF | MU0709_L1800_AE | MUĞLA | 2025-08-29 |  | 2025-10-15 | 2025-10-16 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 20.10.2025 tarihinde cevher girişi yapılmıştır. |  | AQU4518R23v06 | ASI4518R37v07
LTE_New | 56A0QEF | MU0734_L1800_AE | İZMİR | MU0706 STR |  | 2025-12-20 | 2025-12-29 | 8.09.2025 tarihinde gelen malzemeler MU0706 sahasına str yapıldı . | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | ASI4518R37v07 | COMBA
LTE_New | 56A0QEF | MU2494_L1800_AE | MUĞLA | 2025-08-22 |  | 2025-11-21 | 2025-11-21 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 14.09.2025 tarihinde cevher girişi yapılmıştır. |  | ASI4518R37v07 | AOC4518R23v06
LTE_New | 56A0QEF | MU2531_L1800_AE | İZMİR | 2025-08-29 |  | 2025-10-27 | 2025-10-27 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 20.10.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
LTE_New | 56A0QEF | MU2645_L1800_AE | MUĞLA | 2025-09-12 | ŞİMŞEK HABERLEŞME | 2025-09-08 | 2025-09-11 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | Btk eklenecek |  | 27.09.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
LTE_New | 56A0QEF | MU3635_L1800_AE | MUĞLA | 2025-08-21 |  | 2025-12-03 | 2025-12-18 | Kazı yapıldı. | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00
LTE | 56A0QEF | AI0053_L2100_AE | AYDIN | 2025-09-18 |  | 2025-11-15 | 2025-11-28 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | AOC4518R37v06
LTE | 56A0QEF | AI0117_L2100_AE | AYDIN | 2025-09-18 | HASAN TÜRÜDÜ | 2025-10-18 | 2025-10-18 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | BTK YOK | AOC4518R37v06
LTE | 56A0QEF | AI0210_L2100_AE | AYDIN | 2025-09-18 |  | 10.11.205 | 2025-11-14 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | GDI2-065R15M19JJ02-Q-21
LTE | 56A0QEF | AI0267_L2100_AE | AYDIN | 2025-09-18 | HASAN TÜRÜDÜ | 2025-11-24 | 2025-11-25 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00
LTE | 56A0QEF | AI1178_L2100_AE | AYDIN | 2025-09-18 |  | 2025-11-18 | 2025-11-19 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | GDI2-065R15M19JJ02-Q-21 | AOC4518R37v06
LTE | 56A0QEF | AI3068_L2100_AE | AYDIN | 2025-09-18 |  | 2025-11-15 | 2025-11-19 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | BTK HENÜZ YOK | AOC4518R37v06
LTE | 56A0QEF | AI3300_L2100_AE | AYDIN | 2025-09-18 |  | 2025-11-13 | 2025-11-28 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | Batuhan bey kontrol etti | AOC4518R37v06
LTE | 56A0QEF | MN0124_L2600_AE | MANISA | 2025-09-18 |  | 2025-10-31 | 2025-10-31 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | ASI4518R37v07 | AOC4518R37v06
LTE | 56A0QEF | MN0213_L2100_AE | MANISA | 2025-09-18 |  | 2025-11-03 | 2025-11-03 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | AOC4518R37v06 | GDI2-065R15M19JJ02-Q-21
LTE | 56A0QEF | MN0251_L2100_AE | MANISA | 2025-09-18 |  | 2025-11-01 | 2025-11-01 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | AOC4518R37v06 | GDI2-065R15M19JJ02-Q-21
LTE | 56A0QEF | MN0400_L2100_AE | MANISA | 2025-09-18 |  | 2025-11-24 | 2025-11-25 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00
LTE | 56A0QEF | MN0461_L2100_AE | MANISA | 2025-09-18 |  | 2025-11-13 | 2025-11-14 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | AOC4518R37v06 | GDI2-065R15M19JJ02-Q-21
LTE_New | 56A0QEF | MN0426_L1800_AE | MANISA | 2025-10-21 |  | 2025-11-12 | 2025-11-14 |  | ŞİMŞEK HABERLEŞME | 2025-10-10 | ALKOM | 2025-11-03 |  | Huawei | 00.00.00 | ALKOM | 2025-12-02 | 2025-12-03 |  | WTSS |  |  |  | Cevher girişi 3.12.2025 te yapıldı. | 2025-10-30 | ASI4518R37v07 | AQU4518R23v06
LTE_New | 56A0QEF | MU0706_L1800_AE | İZMİR | MU0734 sahasından str yapıldı | HASAN TÜRÜDÜ | 2025-09-08 | 2025-09-20 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  | 20.11.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | ASI4518R37v07
LTE_New | 56A0QEF | MU1069_L1800_AE | İZMİR | MU2494 sahasından str yapıldı | HASAN TÜRÜDÜ | 2025-09-09 | 2025-09-25 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | ASI4518R37v07
LTE | 56A0QEF | IZ1536_L800_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-01 | 2025-10-01 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | COMBA
LTE | 56A0QEF | IZ1165_L800_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-07 | 2025-10-08 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R53v07
LTE | 56A0QEF | IZ1389_L800_AE | İZMİR | 2025-09-18 |  | 2025-11-18 | 2025-11-19 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | AQU4518R23v18
LTE | 56A0QEF | IZ1705_L800_AE | İZMİR | 2025-09-18 |  | 2025-11-07 | 2025-11-07 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R53v07
LTE | 56A0QEF | IZ3230_L800_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-11-15 | 2025-11-15 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R11
LTE | 56A0QEF | IZ2301_L800_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-09 | 2025-10-10 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | ASI4518R11
LTE | 56A0QEF | IZ1919_L800_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-09-27 | 2025-09-27 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | COMBA
LTE | 56A0QEF | IZ1348_L800_AE | İZMİR | 2025-09-18 |  | 2025-11-06 | 2026-02-01 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00
LTE | 56A0QEF | IZ2459_L800_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-13 | 2025-10-13 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | COMBA
LTE | 56A0QEF | IZ3112_L800_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-09 | 2025-10-09 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | ASI4518R37v07
LTE | 56A0QEF | IZ2301_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-09 | 2025-10-10 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | ASI4518R11
LTE | 56A0QEF | IZ1609_L2100_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-07 | 2025-10-08 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | AOC4518R37v06
LTE | 56A0QEF | IZ2459_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-13 | 2025-10-13 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | COMBA
LTE | 56A0QEF | IZ1919_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-09-27 | 2025-09-27 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | COMBA
LTE | 56A0QEF | IZ1900_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-09-30 | 2025-09-30 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | COMBA
LTE | 56A0QEF | IZ5769_L800_AE | İZMİR | 2025-09-18 |  | 2025-10-15 | 2025-10-16 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R53v07
LTE | 56A0QEF | IZ0023_L2600_AE | İZMİR | 2025-09-18 |  | 2025-11-18 | 2025-11-19 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R31v06
LTE | 56A0QEF | IZ3328_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-13 | 2025-10-13 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | AOC4518R37v06
LTE | 56A0QEF | IZ3112_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-09 | 2025-10-09 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK | [5 empty] | ASI4518R37v07
LTE | 56A0QEF | IZ2235_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-09-30 | 2025-09-30 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | OK |  |  |  |  | BTK YOK | COMBA
LTE | 56A0QEF | IZ2286_L2600_AE | İZMİR | 2025-09-18 |  | 2025-10-21 | 2025-10-21 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [5 empty] | BTK YOK | COMBA
LTE | 56A0QEF | IZ1348_L2600_AE | İZMİR | 2025-09-18 |  | 2025-11-06 | 2026-02-01 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00
LTE | 56A0QEF | IZ3187_L2600_AE | İZMİR | 2025-09-18 |  | 2025-10-14 | 2025-10-16 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | AOC4518R37v06
LTE | 56A0QEF | IZ3230_L2600_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-11-15 | 2025-11-15 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R11
LTE | 56A0QEF | IZ0464_L2100_AE | İZMİR | 2025-09-18 | MURAT YAZICI | 2025-10-09 | 2025-10-10 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 | [6 empty] | ASI4518R37v07
LTE_New | 56A0QEF | MU2497_L1800_AE | MUĞLA | 2025-09-26 |  | 2025-12-23 | 2025-12-29 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | 00.00.00 | 00.00.00 |  |  |  | 22.09.2025 tarihinde cevher girişi yapılmış. |  | ASI4518R37v07 | COMBA
LTE_New | 56A0QEF | IZ1548_L1800_AE | İZMİR | 2025-11-29 |  | 2025-12-14 | 2025-12-15 |  | ŞİMŞEK HABERLEŞME | 2025-10-20 | ALKOM | 2025-10-21 | 2025-11-03 | Huawei | 00.00.00 | ALKOM | 2026-01-23 | 2026-01-27 | OK |  |  |  |  | 28.01.2026 cevher girişi yapıldı | 2025-10-30 | ASI4518R37v07
LTE_New | 56A0QEF | IZ6427_L1800_AE | İZMİR | 2025-12-04 |  | 2025-12-12 | 2025-12-25 |  | ŞİMŞEK HABERLEŞME | 2025-10-20 | ALKOM | 2025-10-21 | 2025-11-04 | Huawei | 00.00.00 | ALKOM | 2026-01-16 | 2026-01-20 |  | WTSS |  |  |  | 20.01.2026 tarihinde cevher girişi yapılmıştır. | 30.10.2025/30.12.2025 tarihinde 2 kez dosya hazırlandı ödeme yapıldı | AOC4518R37v06 | AOC4518R37v06
LTE_New | 56A0QEF | IZ1451_L1800_AE | İZMİR | 2025-10-21 |  | 2025-11-12 | 2025-11-12 |  | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | Huawei | 00.00.00 | Huawei | 00.00.00 | 00.00.00 | OK | 00.00.00 |  |  |  | 26.10.2025 te cevher girişi yapılmış. |  | ASI4518R37v07 | AOC4518R37v06

## 5G
Site Type | Project Code | Site Code | İL | Malzeme Status | RF Subcon | RF Started Date | RF Finished Date | RF Note | TSS Subcon | TSS Prepared | TSSR Subcon | TSSR Prepared(Sent to HW) | TSSR Approved | LOS Subcon | BTK Subcon | BTK Prepared | BTK Approved | GS Status | Atlas Status | AsBuilt | Acceptance Docs | PAC | Survey Note | HAKKEDİŞ | BTK ANTEN | MONTAJ ANTEN
5G | 56A0TCT | US3008_NR3500_AE |  | OK | Ubs | OK | OK
5G | 56A0TCT | US3008_NR700_AE |  | NOK
5G | 56A0TCT | US3008_TRP_MB_AE |  | OK |  |  |  | Plan Yapılacak
5G | 56A0TCT | IZ3159_NR3500_AE |  | OK | 2kx | OK | OK | PO Bekler. STR yapıldı. IZ2781den.
5G | 56A0TCT | US0030_NR3500_AE |  | OK | Ubs | Ok | Ok
5G | 56A0TCT | US0030_L2100_AE |  | NOK
5G | 56A0TCT | US0201_NR3500_AE |  | OK | 2kx | Ok | Ok
5G | 56A0TCT | IZ1364_NR3500_AE |  | OK | 2kx | Ok | Ok
5G | 56A0TCT | IZ0671_NR3500_AE |  | OK | Şimşek | OK | Ok
5G | 56A0TCT | AI5130_NR3500_AE |  | OK | Şimşek | OK | Ok
5G | 56A0TCT | US4610_NR3500_AE |  | OK | Şimşek | OK | OK
5G | 56A0TCT | US0075_NR3500_AE |  | OK | Şimşek | OK | OK
5G | 56A0TCT | US0154_NR3500_AE |  | OK | Şimşek | OK | OK
5G | 56A0TCT | US2002_NR3500_AE |  | OK | Şimşek | OK | OK

## DSS
Site Type | Project Code | Project Name | Site Code | Malzeme Status | RF Subcon | RF Started Date | RF Finished Date | RF Note
DSS | 56A0QEF | Turk Telekom Wireless Project | US3008_DSS_AE | OK | 2kx |  |  | Plan yapılacak
DSS | 56A0QEF | Turk Telekom Wireless Project | US0030_DSS_AE | OK | 2kx |  | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | US0201_DSS_AE | OK | 2kx |  | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | MU0062_DSS_AE | OK | Hasan Türüdü |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | MU0378_DSS_AE | OK | Hasan Türüdü |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | MU0636_DSS_AE | OK | Hasan Türüdü |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | MU0698_DSS_AE | OK | Hasan Türüdü |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | MU0420_DSS_AE | OK | Hasan Türüdü |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | MU0108_DSS_AE | OK | Hasan Türüdü |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ2137_DSS_AE | OK | 2kx |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ1284_DSS_AE | OK | 2kx |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ0963_DSS_AE | OK | 2kx |  | OK | PO Bekler
DSS | 56A0QEF | Turk Telekom Wireless Project | US3700_DSS_AE | OK | 2kx |  | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0092_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0250_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI4722_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI1702_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0002_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0224_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0172_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0006_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0212_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI2209_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0196_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ2491_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI4845_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0033_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ3027_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI3217_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0093_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0232_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI4844_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ1209_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI2155_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0302_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0105_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0138_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI4876_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0090_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0060_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | AI0023_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | MU4983_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | MU0018_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ2516_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ0762_DSS_AE | OK
DSS | 56A0QEF | Turk Telekom Wireless Project | IZ1021_DSS_AE | OK |  |  |  | RN tapılacak. Giriş Yok
DSS | 56A0QEF | Turk Telekom Wireless Project | US0218_DSS_AE | OK |  |  |  | Montaja uygun değil. Tip değişmeli
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project
DSS | 56A0QEF | Turk Telekom Wireless Project