## Tum_Isler
Saha Türü | Project Code | Site Code | Item Code | Item Description | Done Qty | Subcon Name | OnAir Date | QC Durum | Kabul Durum | Kabul Not | RF Not
5G | 56A0QEF | ZO1701_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK | as
5G | 56A0QEF | ZO1600_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | ZO0958_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | ZO0937_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | ZO0730_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | ZO0647_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | ZO0553_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | ZO0155_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | ZO0065_DSS_MWA | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | IZ3552_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | IZ3552_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 |  | 04.09.2026 | NOK | NOK | 7,2mt pole nakliyesi
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 |  | 04.09.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | IZ1473_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0TCT | IZ0330_NR3500_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0SJC | ANKDC_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 11.11.2025 | NOK | NOK
5G | 56A0SJC | ANKDC_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 11.11.2025 | NOK | NOK
5G | 56A0SJC | ANKDC_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 11.11.2025 | NOK | NOK
5G | 56A0SJC | ANBAH_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | ANBAH_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | ANBAH_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | ANBAH_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | BYPCI_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | BYPCI_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | BYPCI_5GEXP_ANK | 8812184597 | Antenna Installation,per Pcs | 1 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | BYPCI_5GEXP_ANK | 8812184613 | Antenna Dismantle,per Pcs | 1 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | MALIK_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 11.07.2025 | OK | NOK
5G | 56A0SJC | MALIK_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 11.07.2025 | OK | NOK
5G | 56A0SJC | MALIK_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 11.07.2025 | OK | NOK
5G | 56A0SJC | OSMAE_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 11.03.2025 | OK | NOK
5G | 56A0SJC | OSMAE_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 11.03.2025 | OK | NOK
5G | 56A0SJC | OSMAE_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 11.03.2025 | OK | NOK
5G | 56A0SJC | SINOS_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 12.04.2025 | OK | NOK
5G | 56A0SJC | SINOS_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 12.04.2025 | OK | NOK
5G | 56A0SJC | SINOS_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 12.04.2025 | OK | NOK
5G | 56A0SJC | TEMEL_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 12.12.2025 | OK | NOK
5G | 56A0SJC | TEMEL_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 12.12.2025 | NOK | NOK
5G | 56A0SJC | TEMEL_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 12.12.2025 | OK | NOK
5G | 56A0SJC | YENIL_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 12.01.2025 | OK | NOK
5G | 56A0SJC | YENIL_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 12.01.2025 | OK | NOK
5G | 56A0SJC | YENIL_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 12.01.2025 | NOK | NOK
5G | 56A0SJC | YENIL_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 12.01.2025 | OK | NOK
5G | 56A0SJC | YKTOK_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 11.11.2025 | OK | NOK
5G | 56A0SJC | YKTOK_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 11.11.2025 | OK | NOK
5G | 56A0SJC | YKTOK_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 11.11.2025 | OK | NOK
5G | 56A0TCT | ES0321_NR3500_MWA | 8812184927 | Site as-built documentation, Per site | 1 | Ender Teke | 02.01.2026 | NOK | NOK
5G | 56A0QEF | AT2491_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI4845_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI4845_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI4845_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI4844_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI4844_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI4844_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI1702_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI1702_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI1702_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI0172_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI0172_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0QEF | AI0172_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 |  | 04.09.2026 | NOK | NOK
5G | 56A0TCT | ES4345_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 02.09.2026 | OK | NOK
5G | 56A0TCT | ES4345_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 02.09.2026 | OK | NOK
5G | 56A0TCT | ES4345_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 02.09.2026 | OK | NOK
5G | 56A0TCT | ES4345_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 02.09.2026 | OK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184599 | Additional RRU Installation without FO cable and DC cable, per Pcs | 6 | Federal | 02.09.2026 | OK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184609 | RRU dismantling without any cabling,per Pcs | 6 | Federal | 02.09.2026 | OK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 19.02.2026 | OK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 19.02.2026 | OK | NOK
5G | 56A0TCT | ES4316_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 19.02.2026 | OK | NOK
5G | 56A0TCT | ES4316_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 19.02.2026 | OK | NOK
5G | 56A0TCT | ES0301_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 03.04.2026 | OK | NOK
5G | 56A0TCT | ES0301_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 03.04.2026 | OK | NOK
5G | 56A0TCT | ES0263_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 03.06.2026 | OK | NOK
5G | 56A0QEF | KA3032_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | KA3032_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | KA0079_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | KA0079_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES5042_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES5042_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES4043_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES4043_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0145_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0145_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0048_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0048_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0044_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0044_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | DU2925_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | DU2925_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | DU2911_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Kasım Evin | 04.07.2026 | OK | NOK
5G | 56A0QEF | DU2911_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Kasım Evin | 04.07.2026 | OK | NOK
5G | 56A0QEF | DU0019_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Kasım Evin | 04.07.2026 | OK | NOK
5G | 56A0QEF | DU0019_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Kasım Evin | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0940_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0940_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0070_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0070_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0060_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0060_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0055_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0055_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0030_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0030_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Murat Yokuş | 04.07.2026 | OK | NOK
5G | 56A0QEF | BO3831_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | BO3030_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Kasım Evin | 04.07.2026 | OK | NOK
5G | 56A0QEF | BO2136_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Kasım Evin | 04.07.2026 | OK | NOK
5G | 56A0QEF | BO0123_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Kasım Evin | 04.07.2026 | OK | NOK
5G | 56A0QEF | BO0034_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Kasım Evin | 04.05.2026 | NOK | NOK
5G | 56A0QEF | BI0654_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Kasım Evin | 04.05.2026 | OK | NOK
5G | 56A0QEF | ES0392_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0392_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES3038_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES3038_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0047_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0047_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0041_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | ES0041_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0170_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | CN0170_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 |  | 04.07.2026 | OK | NOK
5G | 56A0QEF | BO2121_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 |  | 04.07.2026 | NOK | NOK
5G | 56A0QEF | ES0040_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Ender Teke | 04.07.2026 | NOK | NOK
5G | 56A0QEF | ES0040_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | Ender Teke | 04.07.2026 | OK | NOK
5G | 56A0QEF | AI0232_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Murat Yokuş | 03.11.2026 | OK | NOK
5G | 56A0QEF | AI0232_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 03.11.2026 | OK | NOK
5G | 56A0QEF | AI0232_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Murat Yokuş | 03.11.2026 | OK | NOK
5G | 56A0QEF | AI0212_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Murat Yokuş | 03.12.2026 | OK | NOK
5G | 56A0QEF | AI0212_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 03.12.2026 | NOK | NOK
5G | 56A0QEF | AI0212_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Murat Yokuş | 03.12.2026 | OK | NOK
5G | 56A0QEF | AI0090_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0090_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 03.09.2026 | NOK | NOK
5G | 56A0QEF | AI0090_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0060_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0060_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0060_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0093_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0093_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0093_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0092_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0092_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0092_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Murat Yokuş | 03.09.2026 | OK | NOK
5G | 56A0QEF | AI0092_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Murat Yokuş | 03.04.2026 | OK | NOK
5G | 56A0TCT | BO0008_NR3500_MWA | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Ender Teke | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO1701_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0954_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0730_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0701_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0551_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0155_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0065_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0563_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0937_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0913_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0716_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0647_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0553_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0011_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO1600_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0003_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0958_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO1701_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0958_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0954_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0730_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0701_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0551_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0155_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0065_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0563_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0937_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0913_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0716_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0647_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0553_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0011_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO1600_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0QEF | ZO0003_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.04.2026 | NOK | NOK
5G | 56A0TCT | ES0301_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 03.04.2026 | NOK | NOK
5G | 56A0TCT | ES0301_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 03.04.2026 | NOK | NOK
5G | 56A0TCT | ES0301_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Federal | 03.04.2026 | NOK | NOK
5G | 56A0TCT | ES0377_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | ETAŞ | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0377_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | ETAŞ | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0377_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | ETAŞ | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0355_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | ETAŞ | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0355_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | ETAŞ | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0355_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | ETAŞ | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0311_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 03.04.2026 | NOK | NOK
5G | 56A0TCT | BO0008_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 03.04.2026 | NOK | NOK
5G | 56A0TCT | ES0288_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 03.05.2026 | NOK | NOK
5G | 56A0TCT | ES0288_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 03.05.2026 | NOK | NOK
5G | 56A0TCT | ES0288_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Federal | 03.05.2026 | NOK | NOK
5G | 56A0TCT | BO0008_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 03.04.2026 | NOK | NOK
5G | 56A0TCT | ES0311_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0311_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0311_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0311_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | Şimşek | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0311_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | Şimşek | 03.06.2026 | NOK | NOK
5G | 56A0TCT | ES0311_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 03.06.2026 | NOK | NOK
5G | 56A0TCT | BO0008_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 03.04.2026 | NOK | NOK
5G | 56A0TCT | BO0008_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 03.04.2026 | NOK | NOK
5G | 56A0SJC | HSYUR_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | TEKOV_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | MPERM_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | MANAD_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | LARAH_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | KKOLA_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | FNAKC_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | CIROR_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
5G | 56A0SJC | ANHAC_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 03.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3759_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Serhat Akpınar | 19.02.2026 | NOK | NOK |  | Lampost temeli için kırıcı ile beton kırımı yapılmış, kepçe ile kazı çalışması gerçekleştirilmiş ve hafriyat için kamyon sahada hazır bulundurulmuştur. Çalışma kapsamında yaklaşık 3x3 m kaldırım taşı sökülmüş ve geri montajı yapılmıştır.
5G | 56A0SJC | NAZCA_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KUSME_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KUSKO_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KUSAN_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KUMAR_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 03.05.2026 | NOK | NOK
5G | 56A0SJC | DORIO_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 03.05.2026 | NOK | NOK
5G | 56A0SJC | BUSTU_5GEXP_ANK | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | BEJAN_5GEXP_ANK | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | BAGCA_5GEXP_ANK | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | AFKCO_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | SANDI_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KOADL_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KOZEL_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KOBAS_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KHASD_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KCBEY_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | KARTU_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | IKBAL_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | EREIP_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | AFKCT_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
5G | 56A0SJC | AFERM_5GEXP_KON | 8812184919 | TK Permission Document ,per pcs | 1 | KADRİYE BEGÜMHAN SARAL | 03.05.2026 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 10 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184842 | Supply and Installation Steel Spiral Pipe ,Per M | 20 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 0 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 20 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184699 | Supply and installation Residual Current Circuit Relay For New sites, per Site | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184675 | Project&temporary admission for LV ,per Site | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 40 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184699 | Supply and installation Residual Current Circuit Relay For New sites, per Site | 2 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8818265084 | MW antenna Pole-offset, per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8818264117 | Installation service MW antenna Pole-offset, per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184675 | Project&temporary admission for LV ,per Site | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 40 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184699 | Supply and installation Residual Current Circuit Relay For New sites, per Site | 2 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184592 | DBS/BTS system installation with F.O/DC (4-6 RRU/RFU), per Site | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 15 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184840 | Supply and Installation PVC Pipe including fixing material,Per M | 25 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184699 | Supply and installation Residual Current Circuit Relay For New sites, per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 35 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184684 | LV power supply and connection from power network to Rooftop Site, including Commercial AC connection if necessary all cabling and installation materials (cable, cable duct, clips) including. ,per M | 35 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184675 | Project&temporary admission for LV ,per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184840 | Supply and Installation PVC Pipe including fixing material,Per M | 33 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 40 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184699 | Supply and installation Residual Current Circuit Relay For New sites, per Site | 2 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 12 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8818265084 | MW antenna Pole-offset, per Pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8818264117 | Installation service MW antenna Pole-offset, per Pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184592 | DBS/BTS system installation with F.O/DC (4-6 RRU/RFU), per Site | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8818249053 | Standard Crane usage, per Day | 2 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 40 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184699 | Supply and installation Residual Current Circuit Relay For New sites, per Site | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184675 | Project&temporary admission for LV ,per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8818168496 | Supply and Installation of Digital counter, per pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184675 | Project&temporary admission for LV ,per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 40 | Şimşek | 12.01.2025 | NOK | NOK |  | Sistem topraklama
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184635 | Supply and Installation Camouflage Chimney 6m Height,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK |  | 2.Sec için yapılacak
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184842 | Supply and Installation Steel Spiral Pipe ,Per M | 10 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 15 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 15 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8818265084 | MW antenna Pole-offset, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8818264117 | Installation service MW antenna Pole-offset, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184592 | DBS/BTS system installation with F.O/DC (4-6 RRU/RFU), per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184642 | Supply and installation Non-Standard Camouflage Works (any type and shape of camouflage),per M*M | 48 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818265084 | MW antenna Pole-offset, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818264117 | Installation service MW antenna Pole-offset, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 7.5 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184592 | DBS/BTS system installation with F.O/DC (4-6 RRU/RFU), per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818265065 | 6m LPRT Pole,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
DSS | 56A0QEF | ZO0913_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 0 | 2kx | 03.04.2026 | NOK | NOK
DSS | 56A0QEF | ZO0913_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 0 | 2kx | 03.04.2026 | NOK | NOK
DSS | 56A0QEF | ZO0003_DSS_MWA | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 03.03.2026 | NOK | NOK
DSS | 56A0QEF | ZO0003_DSS_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.03.2026 | NOK | NOK
5G | 56A0TCT | BO0064_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 03.03.2026 | NOK | NOK
5G | 56A0TCT | BO0064_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 03.03.2026 | NOK | NOK
5G | 56A0TCT | BO0064_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 03.03.2026 | NOK | NOK
5G | 56A0TCT | BO0064_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 03.03.2026 | NOK | NOK
5G | 56A0SJC | YSKSD_5GEXP_IZM | 8812184599 | Additional RRU Installation without FO cable and DC cable, per Pcs | 4 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YSKSD_5GEXP_IZM | 8812184609 | RRU dismantling without any cabling,per Pcs | 4 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YSKSD_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YSKSD_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 3 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YSKSD_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YSKSD_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YSKSD_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YKTOK_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YENIL_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YAYDN_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YAYDN_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | YAYDN_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | URLOT_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | URLOT_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | URLOT_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | URLOT_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURKM_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURKM_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURKM_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURKM_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURKM_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURKM_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURKM_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURER_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURER_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TURER_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAL_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAL_5GEXP_ANK | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAL_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAL_5GEXP_ANK | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAL_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAG_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAG_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAG_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAG_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUNAG_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUGIR_5GEXP_MUG | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUGIR_5GEXP_MUG | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUGIR_5GEXP_MUG | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TUGIR_5GEXP_MUG | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TRAYK_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TRAYK_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TRAYK_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TRAYK_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TRAYK_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TRAYK_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TRAYK_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKU_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKU_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKU_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKU_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKU_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKU_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKE_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKE_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKE_5GEXP_IZM | 8812184599 | Additional RRU Installation without FO cable and DC cable, per Pcs | 4 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKE_5GEXP_IZM | 8812184609 | RRU dismantling without any cabling,per Pcs | 4 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKE_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORKE_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORCM_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORCM_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORCM_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORCM_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORCM_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORCM_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORBE_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORBE_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORBE_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORBE_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORBE_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TORBE_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEOSS_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEOSS_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEOSS_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEOSS_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEOSS_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEOSS_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEOSS_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TEMEL_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TAYRN_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TAYRN_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TAYRN_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TAYRN_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TAYRN_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | TAYRN_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SRYKY_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SRYKY_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SRYKY_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SRYKY_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SRYKY_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SOMBE_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SOMBE_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SOMBE_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SOMBE_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SIVHI_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SINOS_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SEMME_5GEXP_IZM | 8812184599 | Additional RRU Installation without FO cable and DC cable, per Pcs | 5 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SEMME_5GEXP_IZM | 8812184609 | RRU dismantling without any cabling,per Pcs | 5 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SEMME_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SEMME_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SEMME_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | SEMME_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURKU_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURKU_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURKU_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURKU_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURKU_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURHV_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURHV_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURHV_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURHV_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PURHV_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PAMKY_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PAMKY_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PAMKY_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PAMKY_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PAMKY_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | PAMKY_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | OSMAE_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ORZES_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ORZES_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ORGTE_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ORGTE_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ORGTE_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ORGTE_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ORGTE_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MAOSA_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MAOSA_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MAOSA_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MAOSA_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MANEV_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MANEV_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MANEV_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MANEV_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MAMRO_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MAMRO_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | MALIK_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUTUR_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUTUR_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUTUR_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUTUR_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUTUR_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUTUR_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KULME_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | ORHAN TEKE | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KULME_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | ORHAN TEKE | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUCAR_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUCAR_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUCAR_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUCAR_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KUCAR_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRSUN_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRSUN_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRSUN_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRSUN_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRSUN_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRKSK_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRKSK_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRKSK_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRKSK_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRKSK_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRCMA_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRCMA_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRCMA_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KRCMA_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem Toprakçı | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKV_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKU_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKU_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKU_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KOSKU_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MEHMET MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KORKL_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KORKL_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KORKL_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KORKL_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KORKL_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KONIS_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KONIS_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KONIS_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KONIS_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KONAK_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KIZHM_5GEXP_ANK | 8818270797 | BBU Removal, Per SITE | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KIZHM_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KIZHM_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KIZHM_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KIZHM_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KFARB_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KESAR_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KESAR_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KESAR_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Çiğdem toprakçı | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KESAR_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMSA_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMSA_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMSA_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMSA_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMSA_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMSA_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMSA_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMGI_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMGI_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMGI_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KEMGI_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KASTD_5GEXP_KON | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KASTD_5GEXP_KON | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KASTD_5GEXP_KON | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KASTD_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | KALKA_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INNOK_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INNOK_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INNOK_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INNOK_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INNOK_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INNOK_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INCSL_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INCSL_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INCSL_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INCSL_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INCSL_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | INCSL_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ILMEV_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ILMEV_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ILMEV_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ILMEV_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ILMEV_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ILMEV_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | GURMA_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | GATAN_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | GATAN_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | GATAN_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | GATAN_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HAKAN MERİÇ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | GAHST_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | GAHST_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | EZGOK_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | EVK5G_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | EVK5G_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | EVK5G_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | EVK5G_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | EVK5G_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | EVK5G_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ETKAV_5GEXP_ANK | 8818249053 | Standard Crane usage, per Day | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ETKAV_5GEXP_ANK | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ETKAV_5GEXP_ANK | 8818265082 | RRU support offset (1m Pole) ,per SET | 2 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ETKAV_5GEXP_ANK | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 2 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ETKAV_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ESTES_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | UĞUR BERK | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ESANE_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ERINO_5GEXP_KON | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ERINO_5GEXP_KON | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ERINO_5GEXP_KON | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ERINO_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ELMAC_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | DOSCP_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | DOSAL_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | DIKDE_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | DIKDE_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | DIKDE_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | DIKDE_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | CUMAR_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BYPCI_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BORCD_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOHAS_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOHAS_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOHAS_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOHAS_5GEXP_IZM | 8812184614 | RF Antenna Optimization Works,per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOHAS_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOGAL_5GEXP_IZM | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOGAL_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOGAL_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOGAL_5GEXP_IZM | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOGAL_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BOGAL_5GEXP_IZM | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BMERT_5GEXP_KON | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BMERT_5GEXP_KON | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BMERT_5GEXP_KON | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BMERT_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BEYSE_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERIZ_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERIZ_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERIZ_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERIZ_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERIZ_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERHA_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERHA_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERHA_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BERHA_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYPO_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYPO_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYPO_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYOC_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYOC_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYOC_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYOC_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYKA_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYKA_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYKA_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYKA_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYKA_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYKA_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAYKA_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAMEV_5GEXP_MUG | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAMEV_5GEXP_MUG | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAMEV_5GEXP_MUG | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | BAMEV_5GEXP_MUG | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYORT_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYORT_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYORT_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYORT_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYIZM_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYIZM_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYIZM_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYIZM_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AYIZM_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ATSAN_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ASULH_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ARAMZ_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTPR_5GEXP_ANT | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTPR_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Murat Bektaş | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTPR_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTPR_5GEXP_ANT | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTOZ_5GEXP_ANT | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTOZ_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTOZ_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANTOZ_5GEXP_ANT | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANKDC_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANHRM_5GEXP_ANT | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANHRM_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANHRM_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANHRM_5GEXP_ANT | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANDEM_5GEXP_ANT | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANDEM_5GEXP_ANT | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANDEM_5GEXP_ANT | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANDEM_5GEXP_ANT | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANBAH_5GEXP_ANK | 8812463188 | TC Wireless Incentive, per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ANBAH_5GEXP_ANK | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | İZTAŞ | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALOSB_5GEXP_IZM | 8812184613 | Antenna Dismantle,per Pcs | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALOSB_5GEXP_IZM | 8812184597 | Antenna Installation,per Pcs | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALOSB_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALOSB_5GEXP_IZM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALOSB_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALOSB_5GEXP_IZM | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALOSB_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | ÇAĞATAY DEMİREL | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALITV_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALITV_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALITV_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALCTR_5GEXP_IZM | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALCTR_5GEXP_IZM | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALCTR_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALCTR_5GEXP_IZM | 8818265082 | RRU support offset (1m Pole) ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALCTR_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALATR_5GEXP_IZM | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALATR_5GEXP_IZM | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALATR_5GEXP_IZM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALATR_5GEXP_IZM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | ALAKO_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AFKUM_5GEXP_KON | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AFKUM_5GEXP_KON | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AFKUM_5GEXP_KON | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0SJC | AFKUM_5GEXP_KON | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
5G | 56A0TCT | IZ2248_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 14.01.2026 | NOK | NOK
5G | 56A0TCT | IZ2248_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 14.01.2026 | NOK | NOK
5G | 56A0TCT | IZ2248_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 14.01.2026 | NOK | NOK
5G | 56A0TCT | US3202_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | US3202_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | US3202_NR3500_AE | 8818286460 | Installation service 4,5m LPRT Pole,per Pcs | 1 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | US3202_NR3500_AE | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | US3202_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | US3202_NR3500_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | US3202_NR3500_AE | 8818286453 | 4,5m LPRT Pole,per Pcs | 1 | Şimşek | 20.01.2026 | NOK | NOK
DSS | 56A0QEF | MU0698_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI0157_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU0734_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3635_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0697_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI4872_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU2497_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1536_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0464_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2301_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2301_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3328_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2459_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2459_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3187_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1132_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI0267_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN0213_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN0400_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN0461_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI3068_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3051_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0023_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ6427_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU2494_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1548_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1389_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ4792_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1630_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU2531_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU0709_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0920_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0294_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0626_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1415_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0978_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0167_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI0066_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3185_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0082_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI5095_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | DE0366_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU1069_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU0706_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU2645_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1348_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1348_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1919_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1919_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1900_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2235_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1609_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1165_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0129_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3112_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3112_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1451_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1705_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0956_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ5769_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI0117_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2286_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3230_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3230_L800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN0426_L1800_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN0124_L2600_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN0251_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI0210_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI3300_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI0053_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI1178_L2100_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | DE5026_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ4308_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2928_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | US1616_L1800_AE(2.LOKASYON) | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | DE0393_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | DE0364_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | DE0340_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU1181_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI5132_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI1117_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI1102_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI1404_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI1000_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ6462_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | US0700_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | US1616_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | US2500_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | US2035_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ6427_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3759_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1548_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3865_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3853_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3852_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3851_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3850_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3849_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3848_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3847_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3845_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MU3844_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN1166_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | MN0426_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ4792_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ3416_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2878_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ2108_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI4872_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AI0157_L1800_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1819_5GREADINESS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1200_5GREADINESS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ1125_5GREADINESS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IZ0159_5GREADINESS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | US1616_NS_AE(2.LOKASYON) | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3865 _NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3853 _NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3852 _NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3851 _NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3850 _NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3849 _NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3848 _NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3845_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3844_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | US1616_NS_AE(2.LOKASYON) | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3865 _NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3853 _NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3852 _NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3851 _NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3850 _NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3849 _NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3848 _NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3845_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3844_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | MU4983_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2ks | 03.06.2026 | NOK | NOK
DSS | 56A0QEF | MU4983_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2ks | 03.06.2026 | NOK | NOK
DSS | 56A0QEF | MU4983_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | 2ks | 03.06.2026 | NOK | NOK
DSS | 56A0QEF | MU1380_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2ks | 03.06.2026 | NOK | NOK
DSS | 56A0QEF | MU1380_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2ks | 03.06.2026 | NOK | NOK
DSS | 56A0QEF | MU1380_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | 2ks | 03.06.2026 | NOK | NOK
DSS | 56A0QEF | MU0698_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 20.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0698_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 20.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0469_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 15.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0469_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0469_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8818278114 | Supply and Installation of metal sheet for Battery Rack, per pcs | 1 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184646 | Indoor DC Cabinet swap including packing and back delivery to the warehouse,per Site | 1 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184601 | Battery cabinet installation including battery installation, per Pcs | 1 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8818278108 | Installation of 7,2m LPRT pole, per set | 1 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184630 | Dismantling existing pole for any type of type and height, per pcs | 0 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184924 | EMR measurement,per Pcs | 0 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | IZ3312_NR3500_AE | 8818278098 | Supply of 7,2m LPRT pole, per set | 1 | Şimşek | 22.01.2026 | NOK | NOK
5G | 56A0TCT | US5210_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 23.01.2026 | NOK | NOK
5G | 56A0TCT | US5210_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 23.01.2026 | NOK | NOK
5G | 56A0TCT | US5210_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 23.01.2026 | NOK | NOK
5G | 56A0TCT | US5210_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 23.01.2026 | NOK | NOK
5G | 56A0TCT | US5210_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 23.01.2026 | NOK | NOK
5G | 56A0TCT | IZ4069_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | IZ4069_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | IZ4069_NR3500_AE | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | IZ4069_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | US0027_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | US0027_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | US0027_NR3500_AE | 8812184646 | Indoor DC Cabinet swap including packing and back delivery to the warehouse,per Site | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | US0027_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | US0027_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | US0027_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 24.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0330_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | 2kx | 26.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0330_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 26.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0330_NR3500_AE | 8812184924 | EMR measurement,per Pcs | 1 | 2kx | 26.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0330_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | 2kx | 26.01.2026 | NOK | NOK
DSS | 56A0QEF | DE2033_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 28.01.2026 | NOK | NOK
DSS | 56A0QEF | DE2033_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 28.01.2026 | NOK | NOK
DSS | 56A0QEF | DE2033_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 28.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8818274549 | New Microwave Installation&Commissioning,Without IDU,For 90cm - 120cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 30 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8812184630 | Dismantling existing pole for any type of type and height, per pcs | 6 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8812184666 | Intercity TE Equipment Transportation With Long Truck 0 < 300 km,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8818265084 | MW antenna Pole-offset, per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8818264117 | Installation service MW antenna Pole-offset, per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 6 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 6 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US2002_NR3500_AE | 8812184646 | Indoor DC Cabinet swap including packing and back delivery to the warehouse,per Site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | 2kx | 02.03.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | 2kx | 02.03.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8812184646 | Indoor DC Cabinet swap including packing and back delivery to the warehouse,per Site | 1 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US3700_NR3500_AE | 8812184646 | Indoor DC Cabinet swap including packing and back delivery to the warehouse,per Site | 1 | Şimşek | 02.03.2026 | NOK | NOK
5G | 56A0TCT | US3700_NR3500_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | 2kx | 02.03.2026 | NOK | NOK
5G | 56A0TCT | US3700_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | 2kx | 02.03.2026 | NOK | NOK
5G | 56A0TCT | US3700_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | 2kx | 02.03.2026 | NOK | NOK
5G | 56A0TCT | US3700_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 02.03.2026 | NOK | NOK
DSS | 56A0QEF | US3700_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 02.03.2026 | NOK | NOK
DSS | 56A0QEF | US3700_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 02.03.2026 | NOK | NOK
DSS | 56A0QEF | US0201_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 02.03.2026 | NOK | NOK
DSS | 56A0QEF | US0201_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 02.03.2026 | NOK | NOK
DSS | 56A0QEF | US0201_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | 2kx | 02.03.2026 | NOK | NOK |  | Farklı zamanda yapıldı
5G | 56A0TCT | US0154_NR3500_AE | 8812184649 | Roof opening&isolation around shelter,,per M*M | 2 | Şimşek | 02.04.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8812184650 | Roof closing&isolation (in case of public reaction, contract cancellation etc.),,per M*M | 2 | Şimşek | 02.04.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 02.04.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | Şimşek | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | US0075_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | US0075_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | HASAN TÜRÜDÜ | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | HASAN TÜRÜDÜ | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | HASAN TÜRÜDÜ | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 3 | HASAN TÜRÜDÜ | 02.04.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US0090_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US0090_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US0090_NR3500_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US0090_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US0090_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | US0090_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 02.05.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 0 | Şimşek | 02.09.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 02.09.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 02.09.2026 | NOK | NOK
5G | 56A0TCT | IZ0671_NR3500_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 12.02.2026 | NOK | NOK |  | 7,2mt pole
5G | 56A0TCT | IZ0671_NR3500_AE | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 3 | Şimşek | 12.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0671_NR3500_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 12.02.2026 | NOK | NOK
5G | 56A0QEF | IZ0671_NR3500_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | Şimşek | 12.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ0963_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ0963_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ0963_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ1284_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ1284_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ1284_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ2137_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ2137_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | IZ2137_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 14.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0108_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 18.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0108_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 18.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0108_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 18.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0420_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 18.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0420_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 18.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0420_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 18.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8818259360 | Supply & installation Reinforced Slab Concrete, per m3 | 3 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8818265084 | MW antenna Pole-offset, per Pcs | 2 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8818264117 | Installation service MW antenna Pole-offset, per Pcs | 2 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 20.02.2026 | NOK | NOK
LTE_NEW | 56A0QEF | IZ3552_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 20.02.2026 | NOK | NOK |  | Envantrer Bekler
5G | 56A0TCT | US3008_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | UBS | 21.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | UBS | 21.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | UBS | 21.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | UBS | 21.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | UBS | 21.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0636_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0636_DSS_AE | 8812184927 | Site as-built documentation, Per site | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0636_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0636_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0378_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0378_DSS_AE | 8812184927 | Site as-built documentation, Per site | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0378_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0378_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0062_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0062_DSS_AE | 8812184927 | Site as-built documentation, Per site | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0062_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0062_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0482_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0482_DSS_AE | 8812184927 | Site as-built documentation, Per site | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0482_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0482_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0040_DSS_AE | 8812184927 | Site as-built documentation, Per site | 0 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0040_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0040_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0040_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 24.02.2026 | NOK | NOK
5G | 56A0TCT | IZ3159_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | 2kx | 23.02.2026 | NOK | NOK
5G | 56A0TCT | IZ3159_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | 2kx | 23.02.2026 | NOK | NOK
5G | 56A0TCT | IZ3159_NR3500_AE | 8812184613 | Antenna Dismantle,per Pcs | 3 | 2kx | 23.02.2026 | NOK | NOK
5G | 56A0TCT | IZ3159_NR3500_AE | 8812184597 | Antenna Installation,per Pcs | 3 | 2kx | 23.02.2026 | NOK | NOK
5G | 56A0TCT | IZ3159_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 23.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0623_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0623_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0623_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | MU0623_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 24.02.2026 | NOK | NOK
5G | 56A0TCT | IZ1473_NR3500_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | 2kx | 01.05.2026 | NOK | NOK
5G | 56A0TCT | IZ1473_NR3500_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | 2kx | 01.05.2026 | NOK | NOK
5G | 56A0TCT | IZ1473_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | 2kx | 01.05.2026 | NOK | NOK
5G | 56A0TCT | IZ1473_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 01.05.2026 | NOK | NOK
5G | 56A0TCT | IZ1473_NR3500_AE | 8812184924 | EMR measurement,per Pcs | 1 | 2kx | 01.05.2026 | NOK | NOK
5G | 56A0TCT | IZ1473_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | 2kx | 01.05.2026 | NOK | NOK |  | Montaj yeniden yapıldı
DSS | 56A0QEF | IZ1473_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 24.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0023_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0023_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0023_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0302_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0302_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0302_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 03.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0841_NR3500_AE | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 03.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0841_NR3500_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 03.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0841_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0841_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
5G | 56A0TCT | IZ0841_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 03.01.2026 | NOK | NOK
LTE | 56A0QEF | IZ0337_L2600_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 03.03.2026 | NOK | NOK
LTE | 56A0QEF | IZ0337_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 03.03.2026 | NOK | NOK
LTE | 56A0TCT | AI0086_TRP_MB_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 03.02.2026 | NOK | NOK
LTE | 56A0TCT | AI0086_TRP_MB_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 03.02.2026 | NOK | NOK
LTE | 56A0TCT | AI0086_TRP_MB_AE | 8818286456 | DC Cable Dismantle (Frequency), Per Pcs | 3 | HASAN TÜRÜDÜ | 03.02.2026 | NOK | NOK
LTE | 56A0TCT | AI0086_TRP_MB_AE | 8812184609 | RRU dismantling without any cabling,per Pcs | 9 | HASAN TÜRÜDÜ | 03.02.2026 | NOK | NOK
LTE | 56A0TCT | AI0086_TRP_MB_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI2155_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI2155_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI2155_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0006_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0006_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0006_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0138_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0138_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 03.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0138_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 03.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI4872_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI4872_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU2548_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU2548_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3759_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3759_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MN1156_NS_AE | 8818278116 | Getting scientific responsibility documents of electrical engineers, per site | 1 | ETK | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | MN1156_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | ETK | 20.02.2026 | NOK | NOK
DSS | 56A0QEF | AI0065_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0223_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0223_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0223_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0219_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0125_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0125_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0125_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0908_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0908_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0901_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0901_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0901_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0500_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0500_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0500_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0219_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0219_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0065_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0065_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0245_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0245_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0245_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0243_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0243_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0243_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI0908_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4146_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4146_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4146_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4054_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4054_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4054_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4866_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 28.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1308_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1308_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1307_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1307_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0235_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.12.2025 | NOK | NOK
DSS | 56A0QEF | AI4866_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 28.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4866_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 28.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1307_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1306_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1306_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1301_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1301_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1301_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0235_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.12.2025 | NOK | NOK
DSS | 56A0QEF | DE0167_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0167_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0166_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE1030_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1030_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1030_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0166_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE0166_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE0166_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE0166_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE0163_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0163_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0163_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4854_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0306_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0303_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE0163_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0149_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0149_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0149_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0149_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0294_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0294_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0294_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0294_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0149_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0294_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | AI4854_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4854_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4850_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4850_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | AI4850_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0087_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0087_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0087_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0048_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0048_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0048_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0048_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0048_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0033_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0033_DSS_AE | 8812184870 | Site survey,per Pcs | 0 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0033_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0033_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0033_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0029_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0029_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0029_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0306_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0306_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0303_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE0303_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.03.2025 | NOK | NOK
DSS | 56A0QEF | DE0163_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0099_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0099_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0099_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0235_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.12.2025 | NOK | NOK
DSS | 56A0QEF | DE0210_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0210_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0210_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE0172_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0172_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0172_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0170_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0170_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0170_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE0167_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | IZ0962_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0962_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0088_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0088_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0088_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0088_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | DE5218_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE5039_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5039_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5036_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5036_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | IZ0586_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 18.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0586_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 18.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0586_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 18.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0579_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0579_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0579_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0578_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 24.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0578_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 24.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0341_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0341_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0341_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0324_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | UBS EKİP | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0324_DSS_AE | 8812184870 | Site survey,per Pcs | 0 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0578_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 24.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0577_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0577_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0577_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0558_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0558_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0558_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0324_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0324_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0324_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | DE5218_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE5218_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE5206_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5206_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5206_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5116_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5116_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | IZ0530_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 29.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0530_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 29.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0530_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 29.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0262_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0262_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0262_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | DE5116_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5076_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5076_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5076_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5040_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5040_DSS_AE | 8812184870 | Site survey,per Pcs | 0 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5040_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5040_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5040_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE5039_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | IZ0964_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0964_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0964_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0962_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0207_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0207_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0207_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | MURAT YAZICI | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0165_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0165_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0165_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0163_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0163_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0163_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0162_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 11.03.2025 | NOK | NOK
DSS | 56A0QEF | IZ0162_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 11.03.2025 | NOK | NOK
DSS | 56A0QEF | IZ0162_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 11.03.2025 | NOK | NOK
DSS | 56A0QEF | IZ0159_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0159_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0159_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0150_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0150_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0150_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0108_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0108_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0835_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0835_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0835_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0354_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0354_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0354_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ0341_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0341_DSS_AE | 8812184870 | Site survey,per Pcs | 0 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0108_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0833_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 20.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0833_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 20.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0833_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 20.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0809_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0809_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0106_DSS_AE | 8812184927 | Site as-built documentation, Per site | 0 | 2kx | 01.08.2026 | NOK | NOK
DSS | 56A0QEF | IZ0106_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 0 | 2kx | 01.08.2026 | NOK | NOK
DSS | 56A0QEF | IZ0106_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 0 | 2kx | 01.08.2026 | NOK | NOK
DSS | 56A0QEF | IZ0088_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0809_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ0808_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0808_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ0808_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | MURAT YAZICI | 11.05.2025 | NOK | NOK
DSS | 56A0QEF | IZ2317_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2317_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2248_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2248_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2248_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2245_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2245_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2245_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 16.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1558_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 11.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1558_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 11.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1558_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 11.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2219_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 29.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2219_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 29.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2219_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 29.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2191_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2191_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2191_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | HASAN TÜRÜDÜ | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2145_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 18.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2145_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 18.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2145_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 18.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1420_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1200_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1200_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1200_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1199_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2115_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2115_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ2115_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 15.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1199_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1199_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1194_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1194_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1194_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1175_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 11.07.2025 | NOK | NOK
DSS | 56A0QEF | IZ1175_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 11.07.2025 | NOK | NOK
DSS | 56A0QEF | IZ1175_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 11.07.2025 | NOK | NOK
DSS | 56A0QEF | IZ1168_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1168_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1168_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1137_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1137_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1137_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1127_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1127_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1127_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2376_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2376_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2376_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2376_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2376_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 19.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ2317_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1018_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1018_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1018_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1001_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1001_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1001_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1420_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1420_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1419_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1419_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1419_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1417_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1417_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1417_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1125_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1125_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1125_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1372_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1372_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1372_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1331_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1331_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1331_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1331_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1331_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 14.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1329_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1329_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1329_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1324_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1324_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | MURAT YAZICI | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1324_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | MURAT YAZICI | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1278_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1278_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1278_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1227_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 16.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1227_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 16.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1227_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 16.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ1067_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1067_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1067_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1058_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1058_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1058_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1057_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1057_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1057_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | Şimşek | 12.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1041_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1041_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ1041_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 10.11.2025 | NOK | NOK
DSS | 56A0QEF | DE4201_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4201_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4201_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4119_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4119_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4119_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3179_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE3028_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3028_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3028_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3015_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE3015_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE3015_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE4025_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4025_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4025_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4016_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4016_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4016_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE4001_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE4001_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE4001_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE3200_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3200_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3200_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3179_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE3179_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE3008_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3008_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3008_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3003_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3003_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE3003_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE1707_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1707_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1707_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1706_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE1706_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE1706_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE1705_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1705_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1705_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1322_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1322_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1322_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1316_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1316_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1316_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1311_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1311_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE1311_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE4108_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE4108_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | DE5036_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | HAKAN MERİÇ | 12.02.2025 | NOK | NOK
DSS | 56A0QEF | DE1308_DSS_AE | 8818270786 | BBU Modernization, Per SITE | 1 | HAKAN MERİÇ | 30.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ5084_DSS_AE | 8812184919 | TK Permission Document ,per pcs | 0 | 2kx | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ5084_DSS_AE | 8812184870 | Site survey,per Pcs | 1 | 2kx | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ5084_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ5084_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ5084_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 22.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ3130_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3130_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3130_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3094_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | UBS EKİP | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ3094_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | UBS EKİP | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ3094_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | UBS EKİP | 19.12.2025 | NOK | NOK
DSS | 56A0QEF | IZ3076_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3076_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3076_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 26.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3060_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3060_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3060_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3059_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3059_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3059_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3040_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3040_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3040_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3004_DSS_AE | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3004_DSS_AE | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | 2kx | 25.11.2025 | NOK | NOK
DSS | 56A0QEF | IZ3004_DSS_AE | 8812184927 | Site as-built documentation, Per site | 1 | 2kx | 25.11.2025 | NOK | NOK
5G | 56A0QEF | US0030_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0QEF | US0030_L2100_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0QEF | US0030_L2100_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
LTE_NEW | 56A0QEF | US0030_L2100_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0030_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0030_NR3500_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0030_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ1364_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 18.02.2026 | NOK | NOK
5G | 56A0TCT | US0030_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR700_AE | 8812184609 | RRU dismantling without any cabling,per Pcs | 6 | UBS | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR700_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | UBS | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_TRP_MB_AE | 8818286456 | DC Cable Dismantle (Frequency), Per Pcs | 3 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_TRP_MB_AE | 8812184609 | RRU dismantling without any cabling,per Pcs | 12 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_TRP_MB_AE | 8812184598 | Additional RRU/RFU installation with all the cabling, per Pcs | 4 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US3008_NR700_AE | 8818286456 | DC Cable Dismantle (Frequency), Per Pcs | 3 | UBS | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ1364_NR3500_AE | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ1364_NR3500_AE | 8818265065 | 6m LPRT Pole,per Pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0671_NR3500_AE | 8818278108 | Installation of 7,2m LPRT pole, per set | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8818278108 | Installation of 7,2m LPRT pole, per set | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0671_NR3500_AE | 8818278098 | Supply of 7,2m LPRT pole, per set | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8818278098 | Supply of 7,2m LPRT pole, per set | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US2002_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0075_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0671_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US2002_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US2002_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0075_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0075_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0671_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0671_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | AI5130_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US4610_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US2002_NR3500_AE | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US2002_NR3500_AE | 8818265065 | 6m LPRT Pole,per Pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0154_NR3500_AE | 8818265065 | 6m LPRT Pole,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8818278098 | Supply of 7,2m LPRT pole, per set | 3 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8818278108 | Installation of 7,2m LPRT pole, per set | 3 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8812184924 | EMR measurement,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | US0201_NR3500_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8812184919 | TK Permission Document ,per pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
5G | 56A0TCT | IZ0343_NR3500_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 15.02.2026 | NOK | NOK
LTE_NEW | 56A0QEF | IZ1348_L2600_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1348_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ0023_L2600_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IZ3230_L800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ3230_L2600_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IZ1548_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 29.11.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IZ6427_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 12.04.2025 | NOK | NOK
LTE_NEW | 56A0QEF | MN0426_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 21.10.2025 | NOK | NOK
LTE | 56A0QEF | IZ1609_L2100_AE | 8812184609 | RRU dismantling without any cabling,per Pcs | 6 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1609_L2100_AE | 8812184599 | Additional RRU Installation without FO cable and DC cable, per Pcs | 6 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IZ1451_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 21.10.2025 | NOK | NOK
LTE | 56A0QEF | IZ0337_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | 2kx | 09.01.2025 | NOK | NOK
LTE | 56A0QEF | IZ1609_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ0464_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ0337_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | 2kx | 09.01.2025 | NOK | NOK |  | kontrol
LTE | 56A0QEF | IZ0023_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ3328_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ3230_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK |  | kontrol
LTE | 56A0QEF | IZ3187_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ3112_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ2459_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ2301_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ2286_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ2235_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1919_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1900_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1348_L2600_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK |  | kontrol
LTE | 56A0QEF | IZ3230_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK |  | kontrol
LTE | 56A0QEF | IZ3112_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ2301_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1919_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1705_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1536_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1348_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 0 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1165_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ5769_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ1389_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK |  | kontrol
LTE | 56A0QEF | IZ2459_L800_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE_NEW | 56A0QEF | MU1069_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | HASAN TÜRÜDÜ | 26.09.2025 | NOK | NOK |  | MU2494 sahasından str yapıldı
LTE_NEW | 56A0QEF | MU0706_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | HASAN TÜRÜDÜ | 26.09.2025 | NOK | NOK |  | MU0734 sahasından str yapıldı
LTE_NEW | 56A0QEF | MU2497_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 26.09.2025 | NOK | NOK
LTE | 56A0QEF | MN0124_L2600_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI0267_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI0210_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI0053_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | MN0461_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | MN0400_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | MN0251_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | MN0213_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI3300_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI3068_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI1178_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI0117_L2100_AE | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 18.09.2025 | NOK | NOK
LTE_NEW | 56A0QEF | MU2531_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 29.08.2025 | NOK | NOK
LTE_NEW | 56A0QEF | MU2494_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 22.08.2025 | NOK | NOK |  | kontrol
LTE_NEW | 56A0QEF | MU0734_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 18.09.2025 | NOK | NOK |  | kontrol
LTE_NEW | 56A0QEF | MU0709_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 29.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ0920_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ3185_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ1415_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ1274_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | 2kx | 09.01.2025 | NOK | NOK
LTE | 56A0QEF | IZ1132_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ0978_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ0697_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ3051_L2600_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ0626_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ0294_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ0956_L2600_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | IZ0167_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ0082_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA TEKNOLOJİ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | IZ0129_L2600_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | MURAT YAZICI | 18.09.2025 | NOK | NOK
LTE | 56A0QEF | AI5095_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 21.08.2025 | NOK | NOK
LTE | 56A0QEF | AI0066_L800_AE | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | HASAN TÜRÜDÜ | 21.08.2025 | NOK | NOK
LTE_NEW | 56A0QEF | MU2645_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | ŞİMŞEK HABERLEŞME | 12.09.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IZ4792_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 29.08.2025 | NOK | NOK
LTE_NEW | 56A0QEF | DE0366_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | ŞİMŞEK HABERLEŞME | 09.01.2025 | NOK | NOK
LTE_NEW | 56A0QEF | AI4872_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 09.08.2025 | NOK | NOK |  | kontrol
LTE_NEW | 56A0QEF | AI0157_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | HASAN TÜRÜDÜ | 21.08.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IZ1630_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | MURAT YAZICI | 21.08.2025 | NOK | NOK
LTE_NEW | 56A0QEF | MU3635_L1800_AE | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 21.08.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184639 | Supply and Installation Water Tank Type Camouflage,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818265159 | Monopol Tower Antenna mount/pole aparatus for 3 sector, per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Ş | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 10 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184650 | Roof closing&isolation (in case of public reaction, contract cancellation etc.),,per M*M | 6 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184649 | Roof opening&isolation around shelter,,per M*M | 6 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8818168523 | Any type of site/material/equipment dismantling for RT Site ,per SITE | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818264134 | Monopol Tower Antenna Installation mount/pole aparatus for 3 sector, per SET | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818249053 | Standard Crane usage, per Day | 2 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818264116 | Fence gate&padlock installation service, per PCS | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818168523 | Any type of site/material/equipment dismantling for RT Site ,per SITE | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 2 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184694 | Supply and Installation Roof Exit Cover, Per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818274257 | Plastic grass supply and installation, per m2 | 17 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818264129 | Installation service 4,3m LPRT Pole,per Pcs | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184640 | Camouflage Dismantling (any type and shape of camouflage).Excluding Crane usage,per Site | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818264133 | Welded Panel fence installation service, per meter | 32 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818259360 | Supply & installation Reinforced Slab Concrete, per m3 | 3 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8818278098 | Supply of 7,2m LPRT pole, per set | 2 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 2 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8818278108 | Installation of 7,2m LPRT pole, per set | 2 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818265064 | Welded Panel fence, per meter | 32 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818265085 | 4,3m LPRT Pole,per Pcs | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8818265065 | 6m LPRT Pole,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184635 | Supply and Installation Camouflage Chimney 6m Height,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI5132_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | 2kx | 19.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI5132_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | 2kx | 19.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI5132_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | 2kx | 19.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | HASAN TÜRÜDÜ | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | HASAN TÜRÜDÜ | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | HASAN TÜRÜDÜ | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ3552_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 20.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8818168525 | EHS Site Survey ,Per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818274257 | Plastic grass supply and installation, per m2 | 17 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI5132_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | 2kx | 19.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | MURAT YAZICI | 02.04.2026 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184690 | Energy Line Subscription (Optional) ,per SITE | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 5 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8818265065 | 6m LPRT Pole,per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 4 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI5132_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | 2kx | 19.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI5132_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | 2kx | 19.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI5132_NS_AE | 8812184870 | Site survey,per Pcs | 1 | 2kx | 19.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1117_NS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ6427_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184690 | Energy Line Subscription (Optional) ,per SITE | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184690 | Energy Line Subscription (Optional) ,per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI1102_NS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184690 | Energy Line Subscription (Optional) ,per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1548_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184690 | Energy Line Subscription (Optional) ,per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184690 | Energy Line Subscription (Optional) ,per SITE | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812161896 | Supply Conformity Certificate Service of Construction/Building, per PCS | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184690 | Energy Line Subscription (Optional) ,per SITE | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184597 | Antenna Installation,per Pcs | 4 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1451_NS_AE | 8812184592 | DBS/BTS system installation with F.O/DC (4-6 RRU/RFU), per Site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8818264116 | Fence gate&padlock installation service, per PCS | 0 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 25 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184839 | Supply and Installation PVC Canalette including fixing material, Per M | 25 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 25 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184813 | Supply and installation 42U MW Rack ,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818264116 | Fence gate&padlock installation service, per PCS | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184691 | Supply and Installation Vertical Access Ladder, Per m | 3.5 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184691 | Supply and Installation Vertical Access Ladder, Per m | 3.5 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818264132 | Installation service 8m LPRT Pole,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184848 | Supply and installation Cable Window(ship type of Roxtec),per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184691 | Supply and Installation Vertical Access Ladder, Per m | 3 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184691 | Supply and Installation Vertical Access Ladder, Per m | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8818264133 | Welded Panel fence installation service, per meter | 0 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184848 | Supply and installation Cable Window(ship type of Roxtec),per Pcs | 0 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184842 | Supply and Installation Steel Spiral Pipe ,Per M | 10 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818264124 | RRU standing rack installation service, per PCS | 0 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184632 | Supply and Installation Camouflage Chimney 3m Height,per Pcs | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818264133 | Welded Panel fence installation service, per meter | 17 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818259360 | Supply & installation Reinforced Slab Concrete, per m3 | 7 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8818265072 | Fence gate&padlock, per PCS | 0 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818265072 | Fence gate&padlock, per PCS | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8818265064 | Welded Panel fence, per meter | 0 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818265160 | RRU standing rack ,per PCS | 0 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8818265065 | 6m LPRT Pole,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8818265065 | 6m LPRT Pole,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818265076 | 8m LPRT Pole,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 10 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818265064 | Welded Panel fence, per meter | 34 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184691 | Supply and Installation Vertical Access Ladder, Per m | 2 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184692 | Supply and Installation Walking Ladder With Barrier, Per m | 6 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184696 | Supply and Installation Horizontal Angular Access Ladder, Per m | 2 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184633 | Supply and Installation Camouflage Chimney 4m Height,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0706_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU1069_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2497_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | PAŞA TEKNOLOJİ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 4 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184634 | Supply and Installation Camouflage Chimney 5m Height,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818259360 | Supply & installation Reinforced Slab Concrete, per m3 | 3 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818264133 | Welded Panel fence installation service, per meter | 4 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184634 | Supply and Installation Camouflage Chimney 5m Height,per Pcs | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184632 | Supply and Installation Camouflage Chimney 3m Height,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184634 | Supply and Installation Camouflage Chimney 5m Height,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818264120 | Installation service High Density Lampost (8-10-12 meters / t:6mm) 130km/h ,per pcs | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 3 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 12 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 5 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8818249053 | Standard Crane usage, per Day | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 4 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184675 | Project&temporary admission for LV ,per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 20 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 30 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 40 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184834 | Supply Vertical Electrode(Copper),Per M | 15 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818265075 | High Density Lampost (8-10-12 meters / t:6mm) 130km/h ,per pcs | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818265064 | Welded Panel fence, per meter | 4 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2494_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 0 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2531_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0734_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU0709_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MN0426_NS_AE | 8812184870 | Site survey,per Pcs | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 0 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | DE0366_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | HASAN TÜRÜDÜ | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184597 | Antenna Installation,per Pcs | 4 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU2645_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184597 | Antenna Installation,per Pcs | 3 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | MU3635_NS_AE | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | ŞİMŞEK HABERLEŞME | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ1630_NS_AE | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | MURAT YAZICI | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | AI0157_NS_AE | 8812184870 | Site survey,per Pcs | 1 | Şimşek | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184930 | LOS Site Survey, per Site | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184919 | TK Permission Document ,per pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | IZ4792_NS_AE | 8812184870 | Site survey,per Pcs | 1 | SONER TURAN | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IP0938_L2100_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AT1387_L2600_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IP8700_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 31.12.2025 | NOK | NOK
LTE_NEW | 56A0QEF | AT4595_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | IP0842_L800_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AF0058_L2600_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
LTE | 56A0QEF | AF0119_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
LTE_NEW | 56A0QEF | IP8727_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 01.01.2026 | NOK | NOK
LTE_NEW | 56A0QEF | AT8182_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT4631_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2806_DSS_WM | 8818270786 | BBU Modernization, Per SITE | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2806_DSS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2806_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT1628_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT1628_DSS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT1628_DSS_WM | 8818270786 | BBU Modernization, Per SITE | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | IP1936_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | IP1936_DSS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | IP0933_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0458_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0458_DSS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | IP0933_DSS_WM | 8812210997 | BBU expansion with site visit,per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0458_DSS_WM | 8818270786 | BBU Modernization, Per SITE | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0101_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0101_DSS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0101_DSS_WM | 8818270786 | BBU Modernization, Per SITE | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | IP1936_DSS_WM | 8812210997 | BBU expansion with site visit,per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF4026_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF4026_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF4024_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF4024_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT1753_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT1753_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF3943_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF3943_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF0895_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF0895_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF0046_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF0046_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF1472_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF1472_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2301_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2301_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2301_GPS_WM | 8818270786 | BBU Modernization, Per SITE | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2309_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2309_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0602_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0602_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0196_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT0196_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | BU4103_DSS_WM | 8818270786 | BBU Modernization, Per SITE | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | BU4103_DSS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | BU4103_DSS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT4631_DSS_WM | 8818270786 | BBU Modernization, Per SITE | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT4631_DSS_WM | 8812184697 | Boards addition/replace to the existing BBU, per Site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF8532_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF8532_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF4011_GPS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AF4011_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
DSS | 56A0QEF | AT2491_GPS_WM | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | PAŞA | 31.12.2025 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184642 | Supply and installation Non-Standard Camouflage Works (any type and shape of camouflage),per M*M | 42.4 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184649 | Roof opening&isolation around shelter,,per M*M | 37 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184691 | Supply and Installation Vertical Access Ladder, Per m | 3.5 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184696 | Supply and Installation Horizontal Angular Access Ladder, Per m | 3 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184634 | Supply and Installation Camouflage Chimney 5m Height,per Pcs | 0 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 8 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184597 | Antenna Installation,per Pcs | 4 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8812184650 | Roof closing&isolation (in case of public reaction, contract cancellation etc.),,per M*M | 37 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8944_NS_WM | 8818249053 | Standard Crane usage, per Day | 2 | Şimşek | 15.02.2026 | NOK | NOK
LTE_NEW | 56A0QEF | BU8944_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 15.02.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184592 | DBS/BTS system installation with F.O/DC (4-6 RRU/RFU), per Site | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184696 | Supply and Installation Horizontal Angular Access Ladder, Per m | 7 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184693 | Supply and Installation Barries, Per m | 7 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8818265065 | 6m LPRT Pole,per Pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 10 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 20 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184597 | Antenna Installation,per Pcs | 4 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | BU8946_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 03.01.2026 | NOK | NOK
LTE_NEW | 56A0QEF | BU8946_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek | 03.01.2026 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184642 | Supply and installation Non-Standard Camouflage Works (any type and shape of camouflage),per M*M | 39.24 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_L1800_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_L1800_WM | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_L1800_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 15.01.2025 | NOK | NOK
LTE_NEW | 56A0QEF | AT8296_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 0 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8296_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 0 | Şimşek | 15.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184696 | Supply and Installation Horizontal Angular Access Ladder, Per m | 7 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184693 | Supply and Installation Barries, Per m | 10 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184819 | Supply and installation Star Offset, per Pcs | 2 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8818264135 | Installation service 6m LPRT Pole,per Pcs | 1 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8818265065 | 6m LPRT Pole,per Pcs | 0 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8818274259 | Supply and installation Ground Plate for nonstandart Camouflage | 2.25 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 10 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8416_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek |  | NOK | NOK
LTE_NEW | 56A0QEF | AT8416_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | Şimşek |  | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184634 | Supply and Installation Camouflage Chimney 5m Height,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184600 | TP48200/APM30/RFC/IBBS/TMC/CRC types outdoor cabinet family installation, per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8818249053 | Standard Crane usage, per Day | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184664 | Intercity TE Equipment Transportation With Small Truck 0 < 300 km, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 8 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818265066 | RF antenna Pole-offset, per Pcs | 0 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 0 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8818249053 | Standard Crane usage, per Day | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8227_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184692 | Supply and Installation Walking Ladder With Barrier, Per m | 4 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 2.5 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT4595_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184843 | Supply and Installation Steel Cable Tie,per Pcs | 6 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184846 | Supply and Installation Steel Cable Duct, Per M | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT4595_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184597 | Antenna Installation,per Pcs | 4 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 30 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 20 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184834 | Supply Vertical Electrode(Copper),Per M | 20 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184601 | Battery cabinet installation including battery installation, per Pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 0 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8818249053 | Standard Crane usage, per Day | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818249053 | Standard Crane usage, per Day | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8818249053 | Standard Crane usage, per Day | 3 | Şimşek | 12.01.2025 | NOK | NOK |  | 2.ad Gizleme/Outdoor Cabinet
STANDALONE | 56A0QEF | AT8182_NS_WM | 8818274546 | New Microwave Installation&Commissioning,1*IDU,For 30cm - 60cm Diameter Of 2 pcs Antenna,Per Hop | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184601 | Battery cabinet installation including battery installation, per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184927 | Site as-built documentation, Per site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184700 | Supply and installation Residual Current Circuit Relay For Existing Sites, per Site | 2 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184691 | Supply and Installation Vertical Access Ladder, Per m | 3 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184695 | Supply and Installation EHS Warning Sign, Per Set | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184851 | Supply and installation of Power Meter box,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8818264129 | Installation service 4,3m LPRT Pole,per Pcs | 0 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8702_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184634 | Supply and Installation Camouflage Chimney 5m Height,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184635 | Supply and Installation Camouflage Chimney 6m Height,per Pcs | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | IP8700_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8087_NS_WM | 8812184592 | DBS/BTS system installation with F.O/DC (4-6 RRU/RFU), per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8273_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | PAŞA | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8182_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 0 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8361_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT8163_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 0 | Şimşek | 12.01.2025 | NOK | NOK
STANDALONE | 56A0QEF | AT4595_NS_WM | 8812184591 | DBS/BTS system installation with F.O/DC (1-3 RRU/RFU), per Site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF0133_W2100_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | IP8746_L2100_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | IP1072_L2100_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF0257_W2100_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | IP8749_W2100_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT2126_L800_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT2193_L800_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF4045_L800_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT7041_L800_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT0553_L2600_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT0161_L2600_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT0525_L2600_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT4975_L2600_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT0462_L800_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE_NEW | 56A0QEF | AT8087_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE_NEW | 56A0QEF | AT8361_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE_NEW | 56A0QEF | AT8416_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT0522_L2600_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT2004_L2600_WM | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AT3988_L2600_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF0115_L800_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE_NEW | 56A0QEF | BU8946_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE_NEW | 56A0QEF | BU8944_L1800_WM | 8818274283 | One Band Addition at the same site visit ,per pcs | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | IP0862_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF5000_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF0076_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF0006_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF1205_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF2208_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
LTE | 56A0QEF | AF0098_L900_WM | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | PAŞA | 12.01.2025 | NOK | NOK
5G | 56A0TCT | ES0265_NR3500_MWA | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0265_NR3500_MWA | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0265_NR3500_MWA | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0265_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 0 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0396_NR3500_MWA | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0396_NR3500_MWA | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0396_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0280_NR3500_MWA | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0280_NR3500_MWA | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES0280_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES3138_NR3500_MWA | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES3138_NR3500_MWA | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES3138_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 28.02.2026 | NOK | NOK
5G | 56A0TCT | ES4351_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Federal | 14.02.2026 | NOK | NOK
5G | 56A0TCT | ES4351_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Federal | 14.02.2026 | NOK | NOK
5G | 56A0TCT | ES4351_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 14.02.2026 | NOK | NOK
5G | 56A0TCT | ES4351_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 14.02.2026 | NOK | NOK
5G | 56A0TCT | ES4351_NR3500_MWA | 8818249053 | Standard Crane usage, per Day | 1 | Federal | 14.02.2026 | NOK | NOK
5G | 56A0TCT | ES4351_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 14.02.2026 | NOK | NOK
5G | 56A0TCT | ES4316_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES4316_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES4316_NR3500_MWA | 8812184819 | Supply and installation Star Offset, per Pcs | 0 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES4316_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Federal | 02.09.2026 | NOK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Federal | 02.09.2026 | NOK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8818249053 | Standard Crane usage, per Day | 2 | Federal | 02.09.2026 | NOK | NOK |  | 1 adet vinç hakediş ilerletildi.2. gün için QC ye foto yüklenecek.
5G | 56A0TCT | ES4009_NR3500_MWA | 8818278119 | RF & MW Antenna and RRU dismantling and installation for Pole revisions, per site | 0 | Federal | 02.09.2026 | NOK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 02.09.2026 | NOK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Federal | 02.09.2026 | NOK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Federal | 02.09.2026 | NOK | NOK
5G | 56A0TCT | ES4009_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 02.09.2026 | NOK | NOK
5G | 56A0TCT | ES0321_NR3500_MWA | 8812184834 | Supply Vertical Electrode(Copper),Per M | 0 | Şimşek | 21.02.2026 | NOK | NOK
5G | 56A0TCT | ES0321_NR3500_MWA | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 0 | Şimşek | 21.02.2026 | NOK | NOK
5G | 56A0TCT | ES0321_NR3500_MWA | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 0 | Şimşek | 21.02.2026 | NOK | NOK
5G | 56A0TCT | ES0321_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 0 | Şimşek | 21.02.2026 | NOK | NOK
5G | 56A0TCT | ES0321_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 0 | Şimşek | 21.02.2026 | NOK | NOK
5G | 56A0TCT | ES0321_NR3500_MWA | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 21.02.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 1 | Federal | 29.01.2026 | NOK | NOK |  | HW 1 adet için onay verdi
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 1 | Federal | 29.01.2026 | NOK | NOK |  | HW 1 adet için onay verdi
5G | 56A0TCT | ES5502_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184630 | Dismantling existing pole for any type of type and height, per pcs | 0 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8818278119 | RF & MW Antenna and RRU dismantling and installation for Pole revisions, per site | 0 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5502_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 0 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 0 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 0 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0391_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 27.01.2026 | NOK | NOK
5G | 56A0TCT | ES0274_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 24.02.2026 | NOK | NOK
5G | 56A0TCT | ES0274_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Federal | 24.02.2026 | NOK | NOK
5G | 56A0TCT | ES0274_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Federal | 24.02.2026 | NOK | NOK
5G | 56A0TCT | ES0274_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 24.02.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8818270797 | BBU Removal, Per SITE | 1 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8812184601 | Battery cabinet installation including battery installation, per Pcs | 0 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 88123MGE | GPS equipment,antenna and feeder installation ,per SET | 1 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8818278108 | Installation of 7,2m LPRT pole, per set | 0 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8818278098 | Supply of 7,2m LPRT pole, per set | 0 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5315_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 02.06.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 0 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8818278119 | RF & MW Antenna and RRU dismantling and installation for Pole revisions, per site | 0 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8818278108 | Installation of 7,2m LPRT pole, per set | 0 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8812184630 | Dismantling existing pole for any type of type and height, per pcs | 0 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8818278098 | Supply of 7,2m LPRT pole, per set | 0 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES5309_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 29.01.2026 | NOK | NOK
5G | 56A0TCT | ES4347_NR3500_MWA | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 0 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | ES4347_NR3500_MWA | 8818265082 | RRU support offset (1m Pole) ,per SET | 2 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | ES4347_NR3500_MWA | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 2 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | ES4347_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | ES4347_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | ES4347_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | ES4347_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Şimşek | 20.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184836 | Supply Earthing Busbar(Copper),per Pcs | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8818278108 | Installation of 7,2m LPRT pole, per set | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184630 | Dismantling existing pole for any type of type and height, per pcs | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8818278119 | RF & MW Antenna and RRU dismantling and installation for Pole revisions, per site | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8818278098 | Supply of 7,2m LPRT pole, per set | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4343_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Şimşek | 30.01.2026 | NOK | NOK
5G | 56A0TCT | ES4337_NR3500_MWA | 8812184834 | Supply Vertical Electrode(Copper),Per M | 0 | Şimşek | 23.02.2026 | NOK | NOK |  | 8818274543 kalemine dahil
5G | 56A0TCT | ES4337_NR3500_MWA | 8812184807 | Circuit breaker (fuse) 10 A -100 A ,per PCS | 0 | Şimşek | 23.02.2026 | NOK | NOK |  | 8818274543 kalemine dahil
5G | 56A0TCT | ES4337_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 0 | Şimşek | 23.02.2026 | NOK | NOK |  | 8818274543 kalemine dahil
5G | 56A0TCT | ES4337_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 0 | Şimşek | 23.02.2026 | NOK | NOK |  | 8818274543 kalemine dahil
5G | 56A0TCT | ES4337_NR3500_MWA | 8818274543 | Co-Located Site with Antenna Revision Work ,per site | 1 | Şimşek | 23.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8818249053 | Standard Crane usage, per Day | 1 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES4317_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 03.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8812184599 | Additional RRU Installation without FO cable and DC cable, per Pcs | 6 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8812184609 | RRU dismantling without any cabling,per Pcs | 6 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8812184613 | Antenna Dismantle,per Pcs | 3 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8812184597 | Antenna Installation,per Pcs | 3 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8818265066 | RF antenna Pole-offset, per Pcs | 3 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8818264113 | Installation service RF antenna Pole-offset, per Pcs | 3 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8818249053 | Standard Crane usage, per Day | 1 | Federal | 19.02.2026 | NOK | NOK |  | Vinç fotoğrafları QC ye yüklenmemiş.
5G | 56A0TCT | ES3345_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES3345_NR3500_MWA | 8818274542 | Co-Located Site without Antenna Revision Work ,per site | 1 | Federal | 19.02.2026 | NOK | NOK
5G | 56A0TCT | ES0270_NR3500_MWA | 8818278114 | Supply and Installation of metal sheet for Battery Rack, per pcs | 1 | Şimşek | 12.01.2026 | NOK | NOK
5G | 56A0TCT | ES0270_NR3500_MWA | 8812184601 | Battery cabinet installation including battery installation, per Pcs | 1 | Şimşek | 12.01.2026 | NOK | NOK
5G | 56A0TCT | ES0270_NR3500_MWA | 8812184863 | Supply 3M Brand Marking Label ,per Pcs | 1 | Şimşek | 12.01.2026 | NOK | NOK
5G | 56A0TCT | ES0270_NR3500_MWA | 8818264118 | RRU support offset installation service (1m Pole) ,per SET | 3 | Şimşek | 12.01.2026 | NOK | NOK
5G | 56A0TCT | ES0270_NR3500_MWA | 8812184928 | TK Certificate aluminum plate for printing,per pcs | 0 | Şimşek | 12.01.2026 | NOK | NOK
5G | 56A0TCT | ES0270_NR3500_MWA | 8812184924 | EMR measurement,per Pcs | 0 | Şimşek | 12.01.2026 | NOK | NOK
5G | 56A0TCT | ES0270_NR3500_MWA | 8818265082 | RRU support offset (1m Pole) ,per SET | 3 | Şimşek | 12.01.2026 | NOK | NOK